## Key
Key
Likelihood |  |  |  |  | Impact
Rare | Unlikely | Possible | Likely | Certain | Negligible | Minor | Moderate | Major | Extreme
1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Risk Rating (likelihood * impact)
Low | Moderate | High | Extreme
1-3 | 4-6 | 8-12 | 15-25

## Sheet1
Risk Assessment 1- Pre-Project Risks
Ref | Risk | Cause | Event | Likelihood | Impact | Risk Rating | Mitigations
1 | Connection Disruption | Internet dropping out | Inability to access any non-local resources, ask for help, push commits | 4 | 4 | 16 | Having mobile data tethering ready, having plenty of data available
2 | Language Learning Difficulties | No prior experience, as well as a potential inability or difficulties to pick up new programming languages | Struggle to create any functional code, time for project exponentially increased | 2 | 5 | 10 | Ensure attention is paid, work and practice is completed, ask questions where unsure
3 | Effort Lapse | Overwhelmed, burning out, lazy | Struggle to make any forward progress due to mental blocks | 2 | 4 | 8 | Healthy practices outside of working, ensure information is delivered at an acceptable rate, take breaks, set realistic goals
4 | Computer failure | Dead power supply system in Desktop and Laptop | Inability to complete any meaningful work at all, or access any local resources associated with the project | 1 | 5 | 5 | Acquiring a new Power supploy for the PC, and a new battery / charger for the laptop
5 | Bad application | Testing not enough, or not well enough | Application is unusable and doesn't meet the spec | 3 | 4 | 12 | Acquiring assistance where necessary, thorough testing
Risk Assessment 2- During Project Risks (Incorporates pre-project risks)
Ref | Risk | Cause | Event | Likelihood | Impact | Risk Rating | Mitigations
1 | Scope Reach | Attempting to impliment more features than necessary | Creating confusing and unnecessarily complicated code | 3 | 5 | 15 | Having a clear view of what needs to be done for the project, and sticking to it
2 | Not knowing how to start the project | Having no starting point | Cause confusion and make initial learning curve and coding of the project infinitely more difficult | 5 | 3 | 15 | Ensure attention is paid, work and practice is completed, ask questions where unsure
3 | Overwhelming | Too much information to take in at any one time | Creates stress, anxiety, confusion, and falling behind with the project | 4 | 5 | 20 | Asking for assistance where required, attacking the task in bite size chunks, prioritising what needs to be done correctly
4 | Improper Single Responsibility Principle | Not being competent enough with the language to ensure Single Responsibility | Create bad, messy code, that doesn't meet the standard that it is supposed to | 3 | 3 | 9 | Attempting to adhere to Single responsibility throughout the whole project to the best standard possible
5 | Bad Test Coverage | Not Understanding teting/ not having done enough testing practice | Application has sub-par testing coverage and does not meet the spec | 4 | 1 | 4 | Read through material provided for assistance
Risk Assessment 3- Presentation Risks
Ref | Risk | Cause | Event | Likelihood | Impact | Risk Rating | Mitigations
1 | Unable to Coherently Present Code | A lack of understanding of the parts of the code that I didn't write | Leaves bad impression, makes for a bad presentation | 2 | 5 | 10 | Make a conceded effort to understand all of the code in the project
2 | Being unable to answer questions about the project | A lack of fully understanding the code | Bad presentation, bad impression on the trainers | 2 | 2 | 4 | Honesty